## WBS
Task | Status | Depends On | Effort
1. Database Design & Setup | Done
1.1 Install and configure MySQL on the VM | Done
1.2 Create initial database instance | Done
1.3 Build initial ER diagram | Done
1.4 Revise ER diagram based on feedback | Done
2. Database Implementation | Done
2.1 Create tables based on the ERD | Done
2.2 Insert sample data | Done
2.3 Normalize tables to at least 3NF | Done
2.4 Revise schema/ERD | Done
3. SQL Queries & Access | Done
3.1 Write SELECT queries, single table | Done
3.2 Implement JOIN queries, multi-table | Done
3.3 Data retrieval and modifications | Done
3.4 Build command-line CRUD app, single table | Done
3.5 Extend command-line CRUD to many-to-many | Done
4. Web Integration | Done
4.1 Set up Flask environment | Done
4.2 Serve a static webpage | Done
4.3 Build dynamic page via GET form | Done
5. Flask CRUD - Single Table | Not Started | Task 4 | Medium (2-3 days)
5.1 Build HTML form templates for Create/Update
5.2 Add Flask routes for Create, Read, Update, Delete
5.3 Connect routes to MySQL using parameterized queries
5.4 Test each CRUD operation through the browser
6. Flask CRUD - Many-to-Many | Not Started | Task 5 | Large (1 week)
6.1 Build HTML templates to add/remove OS device links
6.2 Add Flask routes for the join-table operations
6.3 Reuse/adapt single-table CRUD patterns for the junction table
6.4 Test adding and removing relationships through the browser
7. Database Considerations | Not Started | Tasks 5, 6 | Medium (2-3 days)
7.1 Create a dedicated least privilege MySQL user for the app
7.2 Move credentials out of source; confirm .env is git-ignored
7.3 Add input sanitization/parameterized queries everywhere
7.4 Add basic form validation
8. Repository Cleanup | Not Started | None | Small (1 day)
8.1 Remove unrelated files (HelloWorld.py, stray flask.py, notes.txt)
8.2 git ignore venv/ and __pycache__/
8.3 Organize remaining files into a clear structure
9. Final Presentation / Demo Prep | Not Started | Tasks 6, 7 | Small (1 day)
9.1 Design a walkthrough of the schema and relationships
9.2 Prepare clean sample data for the demo
9.3 Rehearse CRUD flow end-to-end
10. Post-Class Portfolio Polish | Not Started | Task 9 | Medium (2-3 days)
10.1 Write a proper README
10.2 Consider deploying the Flask app somewhere persistent
10.3 Tidy commit history